# DRAFT - Project Timeline (3-Month Delivery)

Total project duration: 3 months

Total agreement duration: 15 months

Current progress/week2:

- Simple Website construction: 16%

- Staff training: 25%

- Managed Email Services (1 year): 17%

## Phase 1: Identification and Problem Analysis

### Week 0

- Official project kick-off.

- Initial meeting to identify Grow Management Consultants’ needs.

- Draft Proposal

- Draft agreement

- Draft SLA

- Implementation proposal

- Making Timeline

- Definition of project objectives:

  - Simple website build

  - Staff training for administrative personnel

  - Managed email services for 1 year

## Phase 2: Research and Information Gathering

### Week 1

- Initial information collection for the website and email services.

- Training Session 1

### Week 2 (current)

- Continued collection of website content.

- Initial client feedback received.

- Homepage design approved.

- Training Session 2

## Phase 3: Solution Design

### Week 3 – Week 4

- Full website design completed.

- Page structure and content layout.

- Basic visual design (wireframes).

- Email services structure defined.

- Training:

  - Training Session 3

  - Training Session 4

## Phase 4: Planning

### Week 5

- Detailed schedule for website build.

- Internal role allocation for CMS management.

- Completion of content planning.

- Training:

  - Training Session 5

## Phase 5: Construction and Prototyping

### Week 6 – Week 8

- Website development (all pages).

- Configuration of the managed email service.

- Review of prototypes with the client.

- Training:

  - Training Session 6

  - Training Session 7

  - Training Session 8 (final)

## Phase 6: Evaluation

### Week 9 – Week 10

- Functional testing.

- Review with stakeholders.

- Corrections and adjustments implemented.

- Training:

  - Training Session 9

  - Training Session 10

## Phase 7: Implementation and Handover

### Week 11 – Week 12

- Website goes live.

- Final activation of the managed email service.

- Delivery of final documentation.

- Handover to the client.

- Project close-out.

## Post-Project Services

### 1. Managed Email Services – 12-Month Ongoing Service

- Ongoing technical support.

- Monitoring and incident resolution.

- Adjustments to configuration as required.

- Quarterly performance reports.

# FINAL - Project Timeline (3-Month Delivery)

Current progress/ week4:

- Simple Website construction: 34%

- Managed Email Services (1 year): 40%

- Staff training: 100%

## Phase 1: Identification and Problem Analysis

### Week 0

- Official project kick-off.

- Initial meeting to identify Grow Management Consultants’ needs.

- Proposal updated

- agreement updated

- SLA updated

- Implementation proposal

- Definition of project objectives:

  - Simple website build

  - Managed email services for 1 year

  - website maintenance for 6 months

## Phase 2: Research and Information Gathering

### Week 1

- Initial information collection for the website and email services.

- Training Session 1

### Week 2

- Continued collection of website content.

- Initial client feedback received.

- Homepage design approved.

- Training Session 2

## Phase 3: Solution Design

### Week 3 – Week 4 (current)

- Review with stakeholders.

- Full website design completed.

- Page structure and content layout.

- Basic visual design (wireframes).

- Email services structure defined.

- Training:

  - Training Session 3

  - Training Session 4 (final)

## Phase 4: Planning

### Week 5

- Review with stakeholders.

- Detailed schedule for website build.

- Internal role allocation for CMS management.

- Completion of content planning.

## Phase 5: Construction and Prototyping

### Week 6 – Week 8

- Review with stakeholders.

- Proposal updated

- agreement updated

  - Exclude staff training

  - Include Website maintenance for 6 months as a Post-Project Service

- SLA updated

- Website development (all pages).

- Configuration of the managed email service.

- Review of prototypes with the client.

## Phase 6: Evaluation

### Week 9 – Week 10

- Review with stakeholders.

- Functional testing.

- Corrections and adjustments implemented.

## Phase 7: Implementation and Handover

### Week 11 – Week 12

- Review with stakeholders.

- Website goes live.

- Final activation of the managed email service.

- Delivery of final documentation.

- Handover to the client.

- Project close-out.

## Post-Project Services

### 1. Managed Email Services – 12-Month Ongoing Service

- Ongoing technical support.

- Monitoring and incident resolution.

- Adjustments to configuration as required.

- Quarterly performance reports.

### 2. Website Maintenance – 6 Months

- Monthly monitoring and updates.

- Minor content updates.

- Technical maintenance, backups and security patches.

- Monthly status reports.