#### Section 2: Action Plan for review of organisational adherence to IP, ethics/conduct and privacy requirements

Activities in order of priority with scrum style:

| Activity | Description | Time frame | Status |
| --- | --- | --- | --- |
| Sprint 1: Review and audit existing IT Biz Solutions IP, Privacy, and Code of Conduct policies against current legislation. | Sprint Planning Phase: Cross-reference current documents with the Privacy Act 1988 and Copyright Act 1968. Add items to the Product Backlog. | Week 1 - 2 | Completed |
| Sprint 2: Draft policy updates and develop the new Grievance Reporting Procedure. | Execution Phase: Ensure updates reflect ICT industry standards (ACS/ITPA). Ensure document formatting follows the company Style Guide (Arial 10pt). | Week 3 - 4 | Completed |
| Sprint 2 additional update: Review digital security and backup procedures based on trainer feedback. | Divya suggested that the USB-based backup process should be updated to ensure consistency with the company’s privacy and security procedures. The backup process was updated to remove routine USB backups and require approved encrypted corporate backup systems or secure cloud storage. | Week 4 | Completed |
| Sprint Review: Submit updated policies and Grievance Procedure to Management for final approval. | Definition of Done (DoD): As per company guidelines, management's final approval will be requested and confirmed via email. | End of Month 1 | In-progress |
| Sprint 3: Create presentation materials and conduct a staff training/information session. | Hold a round-table session. Gather feedback from the team regarding the new IP, privacy, and ethics procedures. | Month 2 | In-progress |
| Sprint 4: Upload all approved documents to the secure corporate file-sharing system. | Verify that the system (cloud Drive/Intranet) is highly secure, confidential, and accessible only to authorised staff. | Month 2 | No |
| Epic 1: Quarterly compliance audit. | Conduct a brief review of incident tickets and system access logs to ensure staff are adhering to the new privacy and ethics policies. | Month 6 (Q2) | No |
| Epic 2: Bi-annual policy review and refinement against new legislative changes. | Review IP and privacy legislation updates. Refine the Product Backlog if changes are needed to the SOE (Standard Operating Environment). | Month 9 (Q3) | No |
| Epic 3: Annual Retrospective and comprehensive staff refresher training. | Annual Sprint Retrospective: Evaluate the effectiveness of the Grievance Procedure and conduct mandatory refresher training for all tech teams. | Month 12 (Q4) | No |