## Cover Page
Project Budget Technological modernisation of software, hardware systems and Design, implementation of a modern website at Boutique Build Australia | Strictly Confidential
Table of Contents
Project Budget
© 2015 to 2023 CFI Education Inc.
This Excel model is for educational purposes only and should not be used for any other reason. All content is Copyright material of CFI Education Inc.
All rights reserved. The contents of this publication, including but not limited to all written material, content layout, images, formulas, and code, are protected
under international copyright and trademark laws. No part of this publication may be modified, manipulated, reproduced, distributed, or transmitted in any
form by any means, including photocopying, recording, or other electronic or mechanical methods, without prior written permission of the publisher,
except in the case of certain noncommercial uses permitted by copyright law.
https://corporatefinanceinstitute.com/

## Project Budget
Project Budget Template
Project Name: Project ABC |  |  |  | Estimated Time |  | =D12+D17+D25+D126+D135 | Estimated Total Cost |  | 5.3 | Over | -5.3
Date: |  |  |  | Actual Time |  | 0 | Actual Total Cost |  | 0
|  | Labour | [5 empty] | Materials | [5 empty] | Overall
WBS | Task Category | Time |  | Wage |  | Total labour cost |  | Units |  | Cost per unit |  | Total Material Cost |  | Total Cost
|  | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
1 | Modernisation of systems and Building a modern Website |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.1 | Initiation |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.1.1 | Evaluation & Recommendations | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.1.2 | Develop Project Charter for each project | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.1.3 | Submit Project Charter for both projects | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.1.4 | Project Sponsor Reviews Project Charter | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.1.5 | Project Charter Signed/Approved | 0 |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.2 | Planning |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.2.1 | Create Preliminary Scope Statement | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.2.2 | Determine Project Team for each project | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.2.3 | Team Modernisation of systems Kickoff Meeting | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.2.4 | Team Building a Modern website Kickoff Meeting | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.2.5 | Develop Project Plan for both projects | 5 |  | 1.06 |  | 5.3 | 0 |  |  |  |  | 0 | 0 | 5.3 | 0 | -5.3
1.2.6 | Submit Project Plan | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.2.7 | Project Plan Approval |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3 | Execution |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1 | Team Modernisation of systems Kickoff Meeting | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.1 | Implementation of new IT infrastructure to the cloud |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.1 | Research cloud platform providers | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.2 | Choose a provider that guarantees scalability, support, and security within your budget | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.1.3 | Track All changes that affect scope and budget |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.4 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.5 | Sign compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.6 | Sign a contract with the provider |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.7 | Evaluate databases in the legacy system | 4 |  | 1.06 |  | 4.24 | 0 |  |  |  |  | 0 | 0 | 4.24 | 0 | -4.24
1.3.1.1.8 | Evaluate core applications and technical requirements |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.9 | Evaluate available plans and configurations |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.10 | Evaluate available infrastructure configurations | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.11 | Evaluate scalability and security options |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.12 | Select the most appropriate infrastructure and configuration | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.1.13 | Acquire necessary licenses | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.1.14 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.15 | Sign compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.16 | Create backups of legacy databases | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.1.17 | Normalize data in legacy databases | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.18 | Migrate databases to the cloud platform | 4 |  | 1.06 |  | 4.24 | 0 |  |  |  |  | 0 | 0 | 4.24 | 0 | -4.24
1.3.1.1.19 | Validate and test migrated data to the cloud | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.20 | Configure the cloud infrastructure | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.21 | Configure scalability and fault tolerance mechanisms | 4 |  | 1.06 |  | 4.24 | 0 |  |  |  |  | 0 | 0 | 4.24 | 0 | -4.24
1.3.1.1.22 | Perform infrastructure testing | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.1.23 | Analyse core application performance |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.24 | Design native versions of core applications | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.25 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.26 | Sign compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.27 | Develop core applications on the cloud |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.1.28 | Deploy core applications in the cloud | 6 |  | 1.06 |  | 6.36 | 0 |  |  |  |  | 0 | 0 | 6.36 | 0 | -6.36
1.3.1.1.29 | Perform functional and performance tests | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.1.30 | Apply security configurations suggested by the vendor | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.1.31 | Perform testing and adjust | 4 |  | 1.06 |  | 4.24 | 0 |  |  |  |  | 0 | 0 | 4.24 | 0 | -4.24
1.3.1.2 | New work devices and implement remote access tools |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.1 | Research enterprise equipment providers in the area | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.2.2 | Choose the provider that guarantees availability, uptime, and support | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.2.3 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.4 | Track All changes that affect scope and budget |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.5 | Sign compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.6 | Sign a contract with the provider |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.7 | Evaluate available hardware configurations | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.2.8 | Select hardware configurations |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.9 | Select the most reputable VPN provider available in the region | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.2.10 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.11 | Sign compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.12 | Sign a contract with the provider |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.13 | Configure access control and authentication | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.2.14 | Test remote connectivity | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.2.15 | Distribute and configure new work devices |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.2.16 | Receive and inventory work devices | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.2.17 | Install the operating system, corporate software, and security tools | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.2.18 | Distribute work devices to staff | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.3 | Staff training and documentation |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.1.3.1 | Design training by modules and include didactic information for easy understanding | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.3.2 | Prepare training sessions, user manuals, and reference guides | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.1.3.3 | Organize training sessions | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.1.3.4 | Conduct training sessions | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.1.3.5 | Collect feedback |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2 | Team Building a Modern website Kickoff Meeting |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1 | Sprint Planning |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.1 | Define product backlog | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.1.2 | Create story points, prioritize tasks, and estimate effort | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.1.3 | Plan Sprints | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.1.4 | Define objectives |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.5 | Define Sprint durations |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.6 | Define deliverables |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.7 | Research appropriate technologies and frameworks for the project | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.1.8 | Design a connection to the cloud database | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.2.1.9 | Create web mock-ups and adjust them with the client | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.2.1.10 | Perform proofs of concept and connection to the cloud database |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.11 | Choose technologies and frameworks | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.1.12 | Review and validate with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.13 | Sign a compliance certificate |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.14 | Acquire licenses |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.1.15 | Sign agreements with suppliers |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2 | Sprint Execution (Iteration) |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.1.1 | Daily Scrum meetings |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.1.2 | UI/UX Design | 4 |  | 1.06 |  | 4.24 | 0 |  |  |  |  | 0 | 0 | 4.24 | 0 | -4.24
1.3.2.2.1.3 | Frontend Development | 5 |  | 1.06 |  | 5.3 | 0 |  |  |  |  | 0 | 0 | 5.3 | 0 | -5.3
1.3.2.2.1.4 | Backend Development | 5 |  | 1.06 |  | 5.3 | 0 |  |  |  |  | 0 | 0 | 5.3 | 0 | -5.3
1.3.2.2.1.5 | Functionality and usability testing | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.2.2.1.6 | Review with the client |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.1.6.1 | Track All changes that affect scope and budget | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.2.1.6.2 | Track resource allocation |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.2 | Sprint Review & Product Demo |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.2.1 | Present Sprint results to the client | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.2.2.2 | Collect feedback and list requested changes | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.2.3 | Sprint Retrospective |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.2.3.1 | Analyse team performance Development | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.2.3.2 | Identification of improvements for the next Sprint |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.3 | Final Integration and Deployment | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.2.3.1.1 | Final site testing |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.3.1.2 | Final client approval | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.3.2 | Deploy of the site to production | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.3.2.3.3 | Apply security policies | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.3.4 | Perform general and security testing | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.4 | Documentation and training | 3 |  | 1.06 |  | 3.18 | 0 |  |  |  |  | 0 | 0 | 3.18 | 0 | -3.18
1.3.2.4.1 | Create and deliver technical documentation, user manuals, and site administration |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.3.2.4.2 | Training the client's marketing team | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.3.2.5 | Develop Building website closure | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.4 | Control |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.4.1 | Project Management Modernisation of systems | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.4.2 | Project Management Building a Modern website |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.4.3 | Project Status Meetings Modernisation of systems |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.4.4 | Project Status Meetings Building a Modern website |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.4.5 | Risk Management Modernisation of systems | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.4.6 | Risk Management Building a Modern website | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.4.7 | Update Project Management Plan Modernisation of systems | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.4.8 | Update Project Management Plan Building a Modern website | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.5 | Closeout project |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
1.5.1 | Audit Procurement | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.5.2 | Audit Security Policies | 2 |  | 1.06 |  | 2.12 | 0 |  |  |  |  | 0 | 0 | 2.12 | 0 | -2.12
1.5.3 | Document Lessons Learned | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.5.4 | Update Files/Records | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.5.5 | Gain Formal Acceptance | 1 |  | 1.06 |  | 1.06 | 0 |  |  |  |  | 0 | 0 | 1.06 | 0 | -1.06
1.5.6 | Archive Files/Documents |  |  | 1.06 |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0

## Scope Elements
No | Unit/Measurement | Element | Total Cost (AUD) | Description
1 | 1 | ICT Team | 24000 | cost of the all team members for 40 days part-time
2 | 5 | Azure VMs | 2000 | Standard settings: 4 vCPU, 16 GB RAM, Win Server 2019 R2
3 | 4 TB | Azure Storage | 0 | Standard Tier
4 | 1 | Azure SQL Managed Instance | 1000 | 250 GB, 8 vCore
5 | 1 | Azure VNet + VPN Gateway | 200 | VPN Gateway Standard
6 | 11 | Azure AD Premium P1 | 110 | $10 per user
7 | 2 TB | Azure Backup & Recovery | 0 | Daily backup, must be purchased separately
8 | 1 | Azure Firewall / NSGs | 150 | Standard security policies
9 | 1 | Azure Monitor + Log Analytics | 150 | 5 GB
10 | 1 | Discharge Windows Server & SQL | 0 | Services included in the Azure contract
11 | 1 | Azure Migrate Services | 0 | Services included in the contract
12 | 1 | Deployment | 0 | Configuration, installation and application deploy | Cost of ICT services | 24000
13 | 1 | Manuals and training | 0 | Services and documents included in the contract | Cost infraestructure IT | 3610
14 | 1 | Mockups, proof of concept | 500 | Demos, mock-ups, concept apps | Cost business software and work devices | 16144.65
15 | 1 | Design (UI/UX) | 0 | Services included in the contract | Cost website development | 1450
16 | 1 | Front-end development | 0 | Services included in the contract
17 | 1 | Back-end development | 0 | Services included in the contract |  | 45204.65
18 | 1 | Cloud + DB integration | 500 | Azure Connection Tools
19 | 1 | Testing and QA | 300 | external validation
20 | 1 | Domain + Hosting | 150 | cost of domain and website hosting
21 | 1 | Xero | 3.5 | Accounting software
22 | 1 | Microsoft Office 365 Business Premium | 32.9 | Office application
23 | 1 | Webroot Secure Anywhere | 8.25 | Anti-virus
24 | 1 | Dropbox Business Advanced | 25 | File management
25 | 1 | Wrike Business | 25 | Project management suite
26 | 11 | Apple iPad 128GB, Wi-Fi and cellular | 809 | for all client staff members
27 | 3 | PC - desktop | 2700 | for all client service staff , Ryzen 5pro
28 | 3 | monitor 27 inch | 1341 | for customer client service officers
29 | 8 | Corporate laptop 15 inch | 11200 | corporate laptos for CEO + managers. Intel ultra 7
|  | Total Cost | 45204.65