## Chart
Activity | O | M | P | E | Dev | Dependence | Risks
1. Develop Project Charter | 2 | 4 | 6 | 4 | 0.66667 | None | Understanding requirements, and lack of software functionalities
2. Submit Project Charters | 1 | 2 | 3 | 2 | 0.33333 | 1 | Delays in internal review
3. Review and approve Project Charters | 2 | 3 | 5 | 3.1667 | 0.5 | 2 | Delays in client approval
4. Create Preliminary Scope Statement | 3 | 5 | 7 | 5 | 0.66667 | 3 | Incomplete or changing requirements
5. Determine project teams | 1 | 2 | 4 | 2.1667 | 0.5 | 4 | Limited staff availability
6. Conduct kickoff meetings | 0.5 | 1 | 1.5 | 1 | 0.16667 | 5 | Lack of support or team-experience, lack of leadership
7. Develop comprehensive project plans | 5 | 8 | 12 | 8.1667 | 1.1667 | 6 | Insufficient information, delays, tight budget
8. Submit and approve project plans | 2 | 4 | 6 | 4 | 0.66667 | 7 | Delays in feedback and approval, delays in delivering the budget
9. Research cloud platform providers | 3 | 5 | 8 | 5.1667 | 0.83333 | 8 | Lack of suitable options, Hidden costs, required licenses, poor support in the region, poor support worldwide
10. Select cloud provider and sign contract | 2 | 4 | 7 | 4.1667 | 0.83333 | 9 | Long negotiations, legal conditions, inadequate attention to contract details and supplier selection, legal or financial risks
11. Evaluate legacy databases and core applications | 4 | 6 | 10 | 6.3333 | 1 | 10 | Complexity and insufficient documentation
12. Evaluate infrastructure configurations and scalability options | 3 | 5 | 8 | 5.1667 | 0.83333 | 10 | Rapid changes in technology, not covering all possible scenarios
13. Select cloud infrastructure configuration | 2 | 4 | 6 | 4 | 0.66667 | 11,12 | Lack of suitable options, costs, delays
14. Acquire necessary licenses | 1 | 2 | 5 | 2.3333 | 0.66667 | 13 | Delays in the purchasing process
15. Create and validate legacy database backups | 2 | 4 | 6 | 4 | 0.66667 | 11 | Backup failures, data loss, lack of storage space
16. Normalise and prepare data for migration | 3 | 5 | 8 | 5.1667 | 0.83333 | 15 | Inconsistent or incomplete data, corrupting data as a result of inadequate backup procedures
17. Migrate databases to the cloud | 4 | 6 | 9 | 6.1667 | 0.83333 | 16 | Migration failures, system outages, loss of information and data integrity
18. Validate and test migrated data | 3 | 5 | 7 | 5 | 0.66667 | 17 | Migration errors, loss of integrity
19. Configure cloud infrastructure | 3 | 5 | 7 | 5 | 0.66667 | 13 | Incorrect configuration, vulnerabilities
20. Implement scalability and fault tolerance | 4 | 6 | 8 | 6 | 0.66667 | 19 | Performance issues, tolerance failures, not covering all possible scenarios
21. Test cloud infrastructure | 2 | 3 | 5 | 3.1667 | 0.5 | 20 | Configuration failures, compatibility issues
22. Design native versions of core applications | 3 | 6 | 9 | 6 | 1 | 18,21 | Poorly defined requirements, Idealising solutions that cannot be implemented, Inaccurate estimate
23. Develop and deploy core applications to cloud | 6 | 10 | 15 | 10.1667 | 1.5 | 22 | Critical bugs, integration errors, loss of information, Difficulty replicating the same functions in the new system
24. Perform performance and functional testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 23 | Incomplete testing, lack of testing resources
25. Apply vendor-recommended security configurations | 2 | 4 | 6 | 4 | 0.66667 | 23 | Incompatibilities, omission of key policies
26. Conduct system-wide testing and make adjustments | 4 | 6 | 9 | 6.1667 | 0.83333 | 24,25 | Integrated problems, failed final tests, system failures due to adjustments, impacting operational tasks
27. Research hardware providers | 2 | 4 | 6 | 4 | 0.66667 | 8 | Options Limited availability, availability issues, limited options and insufficient information, market reliability and stability, warranty compliance
28. Select hardware provider and sign contract | 1 | 3 | 5 | 3 | 0.66667 | 27 | Negotiation delays, stock shortages, inadequate attention to contract details and supplier selection, legal or financial risks
29. Evaluate and select hardware configurations | 2 | 4 | 7 | 4.1667 | 0.83333 | 28 | Technical incompatibilities, poor selection leading to costs associated with reinvesting in improved hardware
30. Select and contract VPN provider | 1 | 2 | 4 | 2.1667 | 0.5 | 8 | Technical restrictions, contractual delays, coordination issues with the supplier leading to cost overruns
31. Configure access control and authentication | 2 | 4 | 6 | 4 | 0.66667 | 30 | Incorrect configuration, unauthorised access
32. Test remote connectivity | 1 | 2 | 4 | 2.1667 | 0.5 | 31 | Unstable connectivity, non-functional VPN
33. Receive and inventory new work devices | 1 | 3 | 5 | 3 | 0.66667 | 29 | Shipping delays, unit shortages, mistakes in logging and handling new devices
34. Install OS, software, and security tools | 3 | 5 | 8 | 5.1667 | 0.83333 | 33 | Installation failures, missing licenses
35. Distribute and configure devices for staff | 2 | 4 | 6 | 4 | 0.66667 | 34,32 | Logistical issues, delays and increased costs due to employee training, hardware incompatibility
36. Design modular training programs | 2 | 4 | 6 | 4 | 0.66667 | 35 | Inadequate content, low acceptance, too much material to cover, complexity of the material, technical language
37. Prepare user manuals and reference guides | 2 | 3 | 5 | 3.1667 | 0.5 | 36 | Incomplete manuals, documentation errors
38. Organise and conduct training sessions | 3 | 5 | 7 | 5 | 0.66667 | 36,37 | Low support, lack of training resources
39. Collect and evaluate feedback | 1 | 2 | 4 | 2.1667 | 0.5 | 38 | Limited feedback, low participation, scattered feedback
40. Define product backlog and story points | 2 | 3 | 5 | 3.1667 | 0.5 | Ninguna (inicio Scrum) | Ambiguous or changing requirements, budget constraints, lack of technology experience, issues with legacy applications
41. Prioritise tasks and estimate effort | 1 | 2 | 4 | 2.1667 | 0.5 | 40 | Poor effort calculation, misalignment
42. Plan Sprints and define goals | 2 | 4 | 6 | 4 | 0.66667 | 41 | Poorly designed sprint, unclear goals
43. Research technologies and frameworks | 2 | 3 | 5 | 3.1667 | 0.5 | 42 | Inadequate or incompatible technology, lack of legacy documentation
44. Design database connection | 3 | 5 | 7 | 5 | 0.66667 | 43 | Connection failures or failed tests, incompatibility, security breaches
45. Design web mockups and adjust with client | 3 | 5 | 8 | 5.1667 | 0.83333 | 43 | Constant changes, poor customer feedback
46. Choose technologies and acquire licenses | 1 | 2 | 4 | 2.1667 | 0.5 | 43 | Hidden maintenance and operating costs, legal delays, periodic subscriptions, cost of personal certifications
47. UI/UX design | 4 | 6 | 9 | 6.1667 | 0.83333 | 45,46 | Unintuitive design, lack of client commitment
48. Frontend development | 5 | 8 | 12 | 8.1667 | 1.1667 | 47,44 | Visual bugs, integration errors
49. Backend development | 5 | 9 | 13 | 9 | 1.3333 | 47,44 | Security breaches, poor coding practices, poor application performance, excessive resource consumption
50. Functionality and usability testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 48,49 | Failed tests
51. Track changes and resource allocation | 1 | 2 | 4 | 2.1667 | 0.5 | 50 | Lack of follow-up, cost overruns, excessive workload, lack of internal training
52. Present Sprint results to client | 1 | 2 | 3 | 2 | 0.33333 | 51 | Client delays, short meetings, insufficient feedback
53. Collect feedback and list changes | 1 | 2 | 4 | 2.1667 | 0.5 | 52 | Vague or contradictory feedback
54. Analyse Sprint performance and identify improvements | 2 | 3 | 5 | 3.1667 | 0.5 | 53 | Failure to identify critical bugs, overestimated development
55. Conduct final testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 54 | Backlog of problems, unresolved bugs
56. Obtain final client approval | 1 | 3 | 5 | 3 | 0.66667 | 55 | Last-minute changes, lack of agreement
57. Deploy site to production | 1 | 2 | 4 | 2.1667 | 0.5 | 56 | Implementation failures, server problems, very strong security integration makes integration tedious
58. Apply security policies | 2 | 3 | 5 | 3.1667 | 0.5 | 57 | Incomplete configurations, access errors, overly strict security policies, delays in adopting security policies
59. Perform security and general testing | 2 | 4 | 6 | 4 | 0.66667 | 58 | Undetected vulnerabilities, insufficient testing
60. Create technical documentation and user guides | 3 | 5 | 7 | 5 | 0.66667 | 57 | Incomplete or outdated documentation
61. Train client’s marketing team | 2 | 4 | 6 | 4 | 0.66667 | 60 | Resistance to change, low support
62. Close website development project | 1 | 2 | 4 | 2.1667 | 0.5 | 61 | Incomplete documentation or deliverables, unmet expectations
63. Hold status meetings for both projects | 0.5 | 1 | 2 | 1.0833 | 0.25 | Continuas | Low participation, lack of follow-up
64. Perform risk management activities | 2 | 3 | 5 | 3.1667 | 0.5 | 63 | Late risk identification, unknown legal risks
65. Update project management plans | 1 | 2 | 3 | 2 | 0.33333 | 64 | Lack of alignment with stakeholders
66. Audit procurement and security policies | 2 | 4 | 6 | 4 | 0.66667 | 65 | Non-compliance, audit errors
67. Document lessons learned | 1 | 2 | 3 | 2 | 0.33333 | 66 | Unhelpful or poorly documented lessons, inappropriate tool,
68. Update and archive project files | 1 | 2 | 4 | 2.1667 | 0.5 | 67 | Loss of information, unbacked-up files
69. Gain formal acceptance from client | 1 | 3 | 5 | 3 | 0.66667 | 68,62 | Client not satisfied with deliverables

## k-Milestones
No. | Milestone | Description | Due Date
1 | Project Charters Approved | All design, software, and hardware proposals were accepted by the client. | 2025-08-05
2 | Kickoff Meetings Conducted | The transition dates to the cloud, as well as the acquisition of licenses, software, and hardware, were carried out in coordination with the client. | 2025-08-08
3 | Project Plans Approved | The Project Plan was approved by the client. | 2025-08-08
4 | Cloud Provider Contract Signed | The cloud service provider accepted and signed the contract of obligations for this project. | 2025-08-12
5 | Cloud Infrastructure Configured | The environment was successfully configured in the cloud, and all necessary access rights and permissions to the administration console were also set up. | 2025-08-20
6 | Databases Successfully Migrated | The environment was successfully configured in the cloud, and all necessary access rights and permissions to the administration console were also set up. | 2025-08-20
7 | Core Applications Deployed to Cloud | The cloud infrastructure and core applications passed integration, load, functionality, and security/attack tests. | 2025-08-28
8 | Devices Distributed and Configured | All laptops, desktops, and iPads were configured with the requested software and remote/cloud connection tools, and were successfully delivered. | 2025-09-01
9 | Training Completed | All training materials and resources were provided, and all training sessions were successfully completed by the client’s employees. | 2025-09-17
10 | First Sprint Completed & Reviewed | Client feedback was received regarding all designs and changes, and work continues with the second sprint. | 2025-08-29
11 | Website Deployed to Production | The website was deployed, and load testing, functionality testing, and security/attack testing were successfully completed. | 2025-09-01
12 | Formal Project Closure | The project is now completed and closed. All cloud infrastructure, core applications, and the website are ready for production use. | 2025-09-29

## QA-baseline
Deliverable | QA Indicator | Acceptable Level
New Cloud-Based IT Infrastructure with Scalable, Fault-Tolerant Core Applications | Infrastructure fully configured, operational, and fault-tolerant; core applications meet performance, security, and functionality standards | Zero critical failures; maximum of 2 minor configuration or performance issues
Modern, High-Quality, Engaging, and Stylish Website | Website meets usability, design, and performance standards; fully functional with no critical bugs; load times optimized | Zero critical defects; maximum of 5 minor defects; page load time ≤ 3 seconds
Remote Access Tools and Fully Distributed Work Devices | All devices correctly configured and connected; remote access tools fully functional and secure | Zero critical connectivity failures; maximum 5% minor configuration issues
Comprehensive Documentation and Training | All documentation complete, accurate, and understandable; staff training delivered and effective | Minimum 90% staff satisfaction; maximum 5% minor documentation errors

## k-Dependences
No. | Depedency
1 | Gain Formal Acceptance of Project Charter
2 | Gain Formal Acceptance of Scope Statement
3 | Gain Formal Acceptance of Project Plans
4 | Formal budget obtaining
5 | Select Cloud Provider and Sign Contract
6 | Migrate Databases to a Cloud platform
7 | Develop and Deploy Core Applications to Cloud platform
8 | Perform System-Wide Testing
9 | Select work devices Provider and Sign Contract
10 | Configure Work Devices
11 | Gain Formal Acceptance of website functionalities
12 | Conduct Final Testing: IT infrastructure and website, and remote connection

## Change-control
Change proposed by the client
Step | Description | Responsible | Proccess
1 | Identify the need for a change | Any Stakeholder | Requestor will submit a completed IT Biz Solutions change request form to the project manager
2 | Log change in the change request register | Project Manager | The project manager will maintain a log of all change requests for the duration of the project
3 | Conduct an evaluation of the change | Project Manager, Project Team, Requestor | The project manager will conduct an evaluation of the impact of the change to cost, risk, schedule, and scope
4 | The project manager will submit the change request and analysis to the CCB for review | Project Manager | Submit change request to Change Control Board (CCB)
5 | Change Control Board decision (CCB) | CCB | The CCB will discuss the proposed change and decide whether or not it will be approved based on all submitted information
6 | Implement change | Project Manager | If a change is approved by the CCB, the project manager will update and re-baseline project documentation as necessary as well as ensure any changes are communicated to the team and stakeholders
Change proposed by us
Step | Description | Responsible | Proccess
1 | Identify the need for a change | Any member of IT Biz Solutions | The requester will meet with the Project Manager to discuss the change proposal before submitting a change request.
2 | Team planning | Project Manager | Requestor will submit a completed IT Biz Solutions change request form to the project manager. The requester will meet with the Project Manager to discuss the proposed change before submitting a change request. Alternatives will also be considered, seeking the lowest possible impact.
3 | Log change in the change request register | Project Manager | The project manager will maintain a log of all change requests for the duration of the project
4 | Conduct an evaluation of the change | Project Manager, Project Team, Requestor | The project manager will conduct an evaluation of the impact of the change to cost, risk, schedule, and scope
5 | The project manager will submit the change request and analysis to the CCB for review | Project Manager | Submit change request to Change Control Board (CCB)
6 | Change Control Board decision (CCB) | CCB | The CCB will discuss the proposed change and decide whether or not it will be approved based on all submitted information
7 | Implement change | Project Manager | If a change is approved by the CCB, the project manager will update and re-baseline project documentation as necessary as well as ensure any changes are communicated to the team and stakeholders

## Comms-control
Communication Type | Description | Frequency | Format | Participants/ Distribution | Deliverable | Owner
Weekly Status Report | Email summary of project status | Weekly | Email | Project Sponsor, Team and Stakeholders | Status Report | Project Manager
Weekly Project Team Meeting | Meeting to review action register and status | Weekly | In Person | Project Team | Updated Action Register | Project Manager
Project Monthly Review (PMR) | Present metrics and status to team and sponsor | Monthly | In Person | Project Sponsor, Team, and Stakeholders | Status and Metric Presentation | Project Manager
Project Gate Reviews | Present closeout of project phases and kickoff next phase | As Needed | In Person | Project Sponsor, Team and Stakeholders | Phase completion report and phase kickoff | Project Manager
Technical Design Review | Review of any technical specialist hardware/software or work associated with the project | As Needed | In Person | Project Team | Demo, Art-concep, Mock-ups Package | Project Manager

## Comms-directory
Name | Title | E mail | Office Phone | Cell Phone
Manuel Sergio Perez E | Senior IT Project Manager | manuel.perez@itbizsolutions.com | (03) 9000 1001 #201 | 0413 782 940
Richard Kuoch | Project Oversight Mentor | richard.kuoch@itbizsolutions.com | (03) 9000 1002 #202 | 0421 665 378
Roland Morris | Assistant Project Manager | roland.morris@itbizsolutions.com | (03) 9000 1003 #203 | 0468 209 451
Zakary Pineda | Hardware Specialist | zakary.pineda@itbizsolutions.com | (03) 9000 1004 #204 | 0415 937 824
Dani Chen | Software Specialist | dani.chen@itbizsolutions.com | (03) 9000 1005 #205 | 0423 118 509
Ben Nguyen | Project Assistant | ben.nguyen@itbizsolutions.com | (03) 9000 1006 #206 | 0456 774 293
Judith Lee | Project Sponsor | judith.lee@boutiquebuild.com.au | (02) 8000 2001 #301 | 0417 503 682
Ishtar Kahn | Business Owner | ishtar.kahn@boutiquebuild.com.au | (02) 8000 2002 #302 | 0428 916 450
Susan Morgan | Customer Service Manager | susan.mor@boutiquebuild.com.au | (02) 8000 2003 #303 | 0469 331 725