# Project Schedule

|  | Initiative | Deliverable / Task | Assigned To | Estimated Hours | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Both | Establish Requirements Repository & Traceability Links | Manuel Perez (BA) | 10 | Month 1 (Week 1) | Approved |
| 2 | 1: Cloud-First SaaS | Workforce Impact Analysis & Workshops | Manuel Perez (BA) | 40 | Month 1 (Weeks 1-2) | Approved |
| 3 | 1: Cloud-First SaaS | Business Requirements Spec (BRD) & Policy Compliance Check | Manuel Perez (BA) | 50 | Month 1-2 (Weeks 3-5) | Approved |
| 4 | Both | Change added: IT Staff & Devs Compliance Certification (Sentrient) | David Chen / Manuel Perez | 5 | Month 2 (Week 5) | Approved (CR) |
| 5 | 1: Cloud-First SaaS | Change added: Sentrient GRC API & Encryption Requirements (CR) | Manuel Perez (BA) | 20 | Month 2 (Weeks 6-7) | Approved (CR) |
| 6 | 2: Hardware Partnerships | Supplier Evaluation, PPSR Check & SLA Matrix | Manuel Perez (BA) | 30 | Month 1 (Weeks 1-2) | Approved |
| 7 | 2: Hardware Partnerships | ERP Integration Requirements Mapping | Manuel Perez (BA) | 40 | Month 1-2 (Weeks 3-5) | Approved |
| 8 | 2: Hardware Partnerships | Change added: Vendor Risk Mgmt. Gateway Setup (Sentrient CR) | Manuel Perez (BA) | 20 | Month 2 (Weeks 6-7) | Approved (CR) |
| 9 | 1: Cloud-First SaaS | Sprint Supervision, UAT & Comm. Plan Execution | Manuel Perez (BA) | 30 | Month 2-3 (Weeks 6-10) | Approved |
| 10 | 2: Hardware Partnerships | Pilot Review Report & Quality Sign-off | Manuel Perez (BA) | 20 | Month 3 (Weeks 9-10) | Approved |
| 11 | Both | BA Performance Review & Interim Evaluation | Divya Sapra / Manuel Perez | 2 | Month 3 (Week 10) | Approved |
| 12 | Professional Dev. | Change added: Agile/Scrum & Async Communication Training | Manuel Perez (BA) | 15 | Month 3 (Week 11-12) | Scheduled |