## Sheet1
Activity | O | M | P | E | Dev | Dependence | Risks
1. Develop Project Charter | 2 | 4 | 6 | 4 | 0.66667 | None | Lack of clarity in requirements
2. Submit Project Charters | 1 | 2 | 3 | 2 | 0.33333 | 1 | Delays in internal review
3. Review and approve Project Charters | 2 | 3 | 5 | 3.1667 | 0.5 | 2 | Delays in client approval
4. Create Preliminary Scope Statement | 3 | 5 | 7 | 5 | 0.66667 | 3 | Incomplete or changing requirements
5. Determine project teams | 1 | 2 | 4 | 2.1667 | 0.5 | 4 | Limited staff availability
6. Conduct kickoff meetings | 0.5 | 1 | 1.5 | 1 | 0.16667 | 5 | Lack of support or team-experience
7. Develop comprehensive project plans | 5 | 8 | 12 | 8.1667 | 1.1667 | 6 | Insufficient information, delays
8. Submit and approve project plans | 2 | 4 | 6 | 4 | 0.66667 | 7 | Delays in feedback and approval
9. Research cloud platform providers | 3 | 5 | 8 | 5.1667 | 0.83333 | 8 | Lack of suitable options
10. Select cloud provider and sign contract | 2 | 4 | 7 | 4.1667 | 0.83333 | 9 | Long negotiations, legal conditions
11. Evaluate legacy databases and core applications | 4 | 6 | 10 | 6.3333 | 1 | 10 | Complexity and insufficient documentation
12. Evaluate infrastructure configurations and scalability options | 3 | 5 | 8 | 5.1667 | 0.83333 | 10 | Rapid changes in technology
13. Select cloud infrastructure configuration | 2 | 4 | 6 | 4 | 0.66667 | 11,12 | Lack of suitable options, costs
14. Acquire necessary licenses | 1 | 2 | 5 | 2.3333 | 0.66667 | 13 | Delays in the purchasing process
15. Create and validate legacy database backups | 2 | 4 | 6 | 4 | 0.66667 | 11 | Backup failures, data loss
16. Normalize and prepare data for migration | 3 | 5 | 8 | 5.1667 | 0.83333 | 15 | Inconsistent or incomplete data
17. Migrate databases to the cloud | 4 | 6 | 9 | 6.1667 | 0.83333 | 16 | Migration failures, system outages
18. Validate and test migrated data | 3 | 5 | 7 | 5 | 0.66667 | 17 | Migration errors, loss of integrity
19. Configure cloud infrastructure | 3 | 5 | 7 | 5 | 0.66667 | 13 | Incorrect configuration, vulnerabilities
20. Implement scalability and fault tolerance | 4 | 6 | 8 | 6 | 0.66667 | 19 | Performance issues, tolerance failures
21. Test cloud infrastructure | 2 | 3 | 5 | 3.1667 | 0.5 | 20 | Configuration failures, compatibility issues
22. Design native versions of core applications | 3 | 6 | 9 | 6 | 1 | 18,21 | Poorly defined requirements
23. Develop and deploy core applications to cloud | 6 | 10 | 15 | 10.1667 | 1.5 | 22 | Critical bugs, integration errors
24. Perform performance and functional testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 23 | Incomplete testing, lack of testing resources
25. Apply vendor-recommended security configurations | 2 | 4 | 6 | 4 | 0.66667 | 23 | Incompatibilities, omission of key policies
26. Conduct system-wide testing and make adjustments | 4 | 6 | 9 | 6.1667 | 0.83333 | 24,25 | Integrated problems, failed final tests
27. Research hardware providers | 2 | 4 | 6 | 4 | 0.66667 | 8 | Options Limited availability, availability issues
28. Select hardware provider and sign contract | 1 | 3 | 5 | 3 | 0.66667 | 27 | Negotiation delays, stock shortages
29. Evaluate and select hardware configurations | 2 | 4 | 7 | 4.1667 | 0.83333 | 28 | Technical incompatibilities, poor selection
30. Select and contract VPN provider | 1 | 2 | 4 | 2.1667 | 0.5 | 8 | Technical restrictions, contractual delays
31. Configure access control and authentication | 2 | 4 | 6 | 4 | 0.66667 | 30 | Incorrect configuration, unauthorized access
32. Test remote connectivity | 1 | 2 | 4 | 2.1667 | 0.5 | 31 | Unstable connectivity, non-functional VPN
33. Receive and inventory new work devices | 1 | 3 | 5 | 3 | 0.66667 | 29 | Shipping delays, unit shortages
34. Install OS, software, and security tools | 3 | 5 | 8 | 5.1667 | 0.83333 | 33 | Installation failures, missing licenses
35. Distribute and configure devices for staff | 2 | 4 | 6 | 4 | 0.66667 | 34,32 | Logistical issues, hardware incompatibility
36. Design modular training programs | 2 | 4 | 6 | 4 | 0.66667 | 35 | Inadequate content, low acceptance
37. Prepare user manuals and reference guides | 2 | 3 | 5 | 3.1667 | 0.5 | 36 | Incomplete manuals, documentation errors
38. Organize and conduct training sessions | 3 | 5 | 7 | 5 | 0.66667 | 36,37 | Low support, lack of training resources
39. Collect and evaluate feedback | 1 | 2 | 4 | 2.1667 | 0.5 | 38 | Limited feedback, low participation
40. Define product backlog and story points | 2 | 3 | 5 | 3.1667 | 0.5 | Ninguna (inicio Scrum) | Ambiguous or changing requirements
41. Prioritize tasks and estimate effort | 1 | 2 | 4 | 2.1667 | 0.5 | 40 | Poor effort calculation, misalignment
42. Plan Sprints and define goals | 2 | 4 | 6 | 4 | 0.66667 | 41 | Poorly designed sprint, unclear goals
43. Research technologies and frameworks | 2 | 3 | 5 | 3.1667 | 0.5 | 42 | Inadequate or incompatible technology
44. Design database connection and conduct PoCs | 3 | 5 | 7 | 5 | 0.66667 | 43 | Connection failures or failed tests
45. Design web mockups and adjust with client | 3 | 5 | 8 | 5.1667 | 0.83333 | 43 | Constant changes, poor customer feedback
46. Choose technologies and acquire licenses | 1 | 2 | 4 | 2.1667 | 0.5 | 43 | Hidden costs, legal delays
47. UI/UX design | 4 | 6 | 9 | 6.1667 | 0.83333 | 45,46 | Unintuitive design, late feedback
48. Frontend development | 5 | 8 | 12 | 8.1667 | 1.1667 | 47,44 | Visual bugs, integration errors
49. Backend development | 5 | 9 | 13 | 9 | 1.3333 | 47,44 | Incomplete logic, performance issues
50. Functionality and usability testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 48,49 | Failed tests, poor user experience
51. Track changes and resource allocation | 1 | 2 | 4 | 2.1667 | 0.5 | 50 | Poor control of Versions, poorly allocated resources
52. Present Sprint results to client | 1 | 2 | 3 | 2 | 0.33333 | 51 | Client unavailable, rejected deliverables
53. Collect feedback and list changes | 1 | 2 | 4 | 2.1667 | 0.5 | 52 | Vague or contradictory feedback
54. Analyse Sprint performance and identify improvements | 2 | 3 | 5 | 3.1667 | 0.5 | 53 | Failure to identify critical bugs
55. Conduct final testing | 3 | 5 | 8 | 5.1667 | 0.83333 | 54 | Backlog of problems, unresolved bugs
56. Obtain final client approval | 1 | 3 | 5 | 3 | 0.66667 | 55 | Last-minute changes, lack of agreement
57. Deploy site to production | 1 | 2 | 4 | 2.1667 | 0.5 | 56 | Implementation failures, server problems
58. Apply security policies | 2 | 3 | 5 | 3.1667 | 0.5 | 57 | Incomplete configurations, access errors
59. Perform security and general testing | 2 | 4 | 6 | 4 | 0.66667 | 58 | Undetected vulnerabilities, insufficient testing
60. Create technical documentation and user guides | 3 | 5 | 7 | 5 | 0.66667 | 57 | Incomplete or outdated documentation
61. Train client’s marketing team | 2 | 4 | 6 | 4 | 0.66667 | 60 | Resistance to change, low support
62. Close website development project | 1 | 2 | 4 | 2.1667 | 0.5 | 61 | Incomplete documentation or deliverables
63. Hold status meetings for both projects | 0.5 | 1 | 2 | 1.0833 | 0.25 | Continuas | Low participation, lack of follow-up
64. Perform risk management activities | 2 | 3 | 5 | 3.1667 | 0.5 | 63 | Late risk identification
65. Update project management plans | 1 | 2 | 3 | 2 | 0.33333 | 64 | Lack of alignment with stakeholders
66. Audit procurement and security policies | 2 | 4 | 6 | 4 | 0.66667 | 65 | Non-compliance, audit errors
67. Document lessons learned | 1 | 2 | 3 | 2 | 0.33333 | 66 | Unhelpful or poorly documented lessons
68. Update and archive project files | 1 | 2 | 4 | 2.1667 | 0.5 | 67 | Loss of information, unbacked-up files
69. Gain formal acceptance from client | 1 | 3 | 5 | 3 | 0.66667 | 68,62 | Client not satisfied with deliverables