## Slide 1: New Website Quality Management Plan
By: Manuel P
Date: 16/10/2026
ICTSAD507 Assessment Task 2: Project Portfolio
Milestones IC | Advance Diploma of IT

## Slide 2: Why quality matters
The SWOT analysis identifies the lack of a clear quality management system as a weakness
The College maintains quality in compliance with the national VET Quality Framework and through its continuous improvement system
Strategic Objective 2: "To establish and maintain high quality infrastructure supporting clients and staff"

## Slide 3: Legislation and benchmarks
Legislation our IT quality processes must support
Privacy Act 1988
Copyright Act 1968 and Copyright (International Protection) Regulations 1969
Australian Consumer Law
Work Health and Safety Act 2011
Corporations Act 2001
Benchmarks
Benchmark | Target
Annual profit increases | 10%
Employee turnover | Less than 10%
Customer complaints | Less than 5
New ideas implemented | 1 each year

## Slide 4: Quality management system and plan
Suitable system: ISO 9000 (ISO 9001), first in the IT department, then across the College
Purpose: This plan provides a formal framework for ensuring quality throughout the new website project. It has two components

## Slide 5: Quality management system and plan
Deliverables: website design, website content, online enrolment form, accounting system integration, students only area/LMS link, IT department training.
Processes: supplier selection, progress meetings and communication with the developer, change control, testing and acceptance, budget and schedule control.

## Slide 6: Quality management system and plan
Process standards
Three quotes are obtained before the developer is engaged.
The developer attends a progress meeting every week, and the minutes are recorded.
Changes to scope, budget or timeframe are approved in writing before they are made.
Issues are recorded in the project issues register within 1 business day.
Timing standards
The website goes live by 30 June 2023.
Spending stays within $10,000, and payments are tracked against milestones.
A status report goes to senior management every month.
IT department training is completed before handover.

## Slide 7: Quality management system and plan
Quality control and assurance activities
Obtain three quotes and confirm the requirements in the developer contract
Hold weekly progress meetings and review progress against the schedule and budget
Apply change control: review and approve change requests
Review the design and content against the Website Design Brief
Test every deliverable against the standards in Section 4 and record the results
User acceptance check by College staff
Evaluate the project and record the lessons learnt

## Slide 8: Quality management system and plan
Pillars
Quality roles and responsibilities
Quality tools
Plan for reporting quality control (identify & corrective action)

## Slide 9: IT Quality Policy
To commitment to quality across all IT activities and ICT systems, aligned with Strategic Objective 2
Policy principles
Fitness for purpose
Legislative compliance
Structured governance and procurement (QMP for every project)
Quality assurance and control (testing before go-live)
Risk and issue management (issues register, corrective action requests)
Continuous improvement and capability (training, benchmarks, yearly review)

## Slide 10: QMP: objectives and deliverables
Quality Objectives:
Modern, responsive website that appeals to younger students
Online enrolments with invoices issued automatically through the accounting system
Students only area linked to the LMS, for authorised users only
Positive user experience, fewer than 5 customer complaints
Delivery by 30 June 2023, within $10,000
IT department trained to maintain the website
Compliance with privacy, copyright, Australian Consumer Law and WHS
Deliverables reviewed: design, content, enrolment form, accounting integration, students only area/LMS, IT training

## Slide 11: QMP: quality standards
Type | Example standards
Performance | 100% of test enrolments submitted and invoiced correctly; 0 broken links; only authorised users access the students only area; HTTPS on all pages
Process | Three quotes; weekly developer meetings with minutes; written approval of changes; issues recorded within 1 business day
Timing | Go-live by 30 June 2023; within $10,000; monthly status report; training before handover
Cannot be compromised: enrolments, invoices, access, links, content, privacy and security
Can be fixed after go-live: minor cosmetic issues in responsive design

## Slide 12: QMP: roles, monitoring and corrective action
Role | Main responsibilities
IT Manager | Owns the plan, single point of contact with the developer, approves changes and CARs
IT Support Officer | Testing, link checks, issues register, test log, status reports
Web developer | Delivers to standards, attends weekly meetings, fixes defects
Senior management | Approves budget, timeframe and scope changes
College staff | Provide and approve content, user acceptance check
Tools: issues register, test plan and log, checklist, meeting minutes, monthly status report, CAR form, complaints log
Corrective action: Identify and record, Analyse, Raise CAR, Approve, Implement, Verify, Close and improve

## Slide 13: Skills to meet quality standards
Which quality-related roles and key tasks can you competently perform on the project?
Are you able to cover each of the following areas of interest?
Are there any skills or knowledge gaps that could affect? training, support or specialist expertise required?
Do you identify with the standards required to ensure that quality objectives are met?

## Slide 14: Questions?
What add, remove or change in the policy or the plan?
roles or responsibilities?
Any no listed Risk?

## Slide 15: THANKS!